## Sheet1
Group 16	Story #	Feature	Sprint Backlog Item	Task	Volunteer	Task Details	Initial Effort Estimate(hrs)		New Estimates of Effort remaining at end of					Status
				Day 1	Day 2	Day3	Day 4	Day 5
	US001	Customer Registration	As an user, I want to register myself / within the system.	Task 1	Radhika	As a new customer, I want to be able to register an account with Electricity Management System / by providing details such as Consumer ID, Customer Name, Email, Mobile Number etc.	3		3	0	0	0	0				Closed

	US002	Administrator Registration	Register an Admin account / programmatically from the backend.	Task 2	Shrihari	Programmer should register an Admin account programmatically from / the backend.	4		2	2	0	0	0				Open

	US003	User Login	As a registered customer, I want to log in to my / account.	Task 3	Radhika	As a registered customer, I want to log in to my account using my / userName and password.	3		0	3	0	0	0				Closed

	US004	View Bills	As a customer, I want to view the list of bills / pending for payment.	Task 4	Aniket	As a customer, I want to view the list of list of bills in the system	3		3	0	0	0	0				Closed

	US005	Pay Bill	As a customer, I want to pay the bills pending for / due.	Task 5	Aniket	As a customer, I want to to pay the bills pending for due.	3		0	3	0	0	0				Closed

	US006	View Bill History	As a customer, I want to view my bill history.	Task 6	Rekha	As a Customer, I want to view my bill history	2		2	0	0	0	0				Open

	US007	Register Complaint	As a customer, I want to be register complaint in / the system	Task 7	Harsh	As a customer, I want to register complaint in the system by / providing details like complaint type, category, consumer id etc	3		3	0	0	0	0				Closed

	US008	Search Complaint	As a customer , I want to search a complaint	Task 8	Harsh	As a customer, I want to search complaint in the system by providing / complaint id.	4		0	2	2	0	0				Closed

	US009	Complaint history	As a customer I want to view the complaints / registered.	Task 9	Rekha	As a Customer, I want to view my complaint history	3		0	3	0	0	0				Open

	US010	Customer Details Update	As a customer, I want to be able to update my / personal details.	Task 10	Shrihari	As a customer, I want to be able to update my personal details.	3		0	1	2	0	0				Open

	US011	Soft Delete Customer Account	As a customer, I want the option to deactivate / my account.	Task 11	Sushant	As a customer, I want the option to deactivate my account without / permanently deleting my information	3		3	0	0	0	0				Closed

	US012	Restore Customer Account	As a customer, I want to be able to restore my / account	Task 12	Sushant	As a customer, I want to be able to restore my previously / deactivated account	2		0	2	0	0	0				Closed

	US013	Code Integration	As a development team working on the electricity billing application, / we want to ensure that all individual code components are integrated	Task 13	All	As a development team working on the electricity billing application, we want to ensure that all individual code components are integrated and work on single DB. This integration will enable us to verify that the different parts of the system work together correctly.	3		0	0	0	3	0				Closed

	US014	Integration Testing	As a consumer, I want to use electricity billing / application and interact with services	Task 14	All	As a consumer, I want to use electricity billing application and / interact with the producer's services seamlessly.	2		0	0	0	2	0				Closed

	US015	Functional Testing	As a developer, I want to perform functional testing	Task 15	All	As a developer, I want to perform functional testing for all user / stories to ensure application functionality.	2		0	0	0	0	2				Closed

				Total	43	43	16	16	4	5	2

## Sheet2
				Sprint timeline / Remaining Effort(in hrs)

Day0	Day1	Day2	Day3	Day4	Day5	Day6
43	16	16	4	5	2	0